ClimAssist

Climate-Health-Agriculture Decision Platform for Katsina State

# The Problem

Katsina State has lost 15% of its forest cover. 60% of farmlands face drought. 75% of the population depends on agriculture. Meanwhile, 77% of severe childhood malaria cases occur May–September, directly correlated with rainfall patterns. Climate data exists but is trapped in global models that no local decision-maker can access or act on.

# The Vision

ClimAssist connects climate projections, health surveillance, and agricultural intelligence into a single decision platform — purpose-built for Katsina State. A farmer in Jibia gets planting guidance based on real climate forecasts. A health officer in Dutsin-Ma gets an 8-week malaria risk forecast. The SA on Climate Change gets an LGA-level dashboard showing where to deploy resources.

## Platform Architecture

ClimAssist — Climate-Health-Agriculture Decision Platform

| Climate Models (ERA5, nextGEMS, DestinE) | Health Records (Malaria, Meningitis, Nutrition) | Agriculture Data (ECOCROP, Soil, Crop Yields) |
| --- | --- | --- |

▼

| Multi-Agent AI Engine (RAG + LLM + Climate Science) | Predictive Analytics (Malaria risk, Crop timing, Drought) |
| --- | --- |

▼

| Farmer Advisory (When/what to plant) | Health Early Warning (8-week malaria forecast) | Policy Dashboard (LGA-level climate risk) |
| --- | --- | --- |

▼

| Katsina State Government (34 LGAs, Extension Workers) | Primary Health Centers (Digitized Health Records) |
| --- | --- |

# What We Build (Phase 1 — 12 Months)

| Climate Engine | Deploy ClimSight for Katsina: localized climate projections, ERA5 ground truth, crop suitability analysis (ECOCROP), scientific literature RAG. Already functional. |
| --- | --- |
| Health Integration | Digitize basic health indicators (malaria cases, malnutrition admissions, respiratory infections) from primary health centers across priority LGAs. Build the climate-health correlation pipeline. |
| Predictive Layer | Train malaria early warning model using ERA5 rainfall (2–3 month lag) + temperature + historical case data. Target: 8-week advance warning at LGA level. |
| Farmer Advisory | SMS/WhatsApp-based planting guidance for extension workers. When to plant, what to plant, fertilizer timing — all driven by climate projections for their specific location. |
| Policy Dashboard | Web dashboard for the SA on Climate Change showing LGA-level risk maps, seasonal outlooks, and intervention tracking aligned with KAGGA targets. |

# Funding Strategy

Google.org AI for Science Challenge (Deadline: April 17, 2026)

$500K–$3M grants for AI projects advancing climate resilience and health. ClimAssist bridges both tracks. Scolo applies as the tech lead; the Office of the SA on Climate Change, Katsina State is the implementation partner.

## Why Katsina, Why Now

- #2 in Nigeria's Climate Governance Ranking — institutional readiness is already proven

- 30 bankable climate projects presented at COP30 — the mandate exists

- 30% state budget pledged to climate resilience — funding commitment is real

- Africa's first subnational Green Public Procurement EO — policy innovation is happening

Next Step

We deploy a customized ClimAssist instance for Katsina State within 4 weeks. Professor Al-Amin’s office provides priority LGAs and health facility contacts. Scolo configures the platform and submits the Google.org application by April 17.

Abdulhakim Gafai  |  Scolo  |  abdulhakim.gafai@gmail.com